## Project schedule
| IN2033 Project | [5 empty] | Project start: | [7 empty] | 2026-01-26
| MediFlow Solutions |  | Project lead: Dawud |  |  |  | Display week: | [7 empty] | 7
[7 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-03-09 to 2026-05-03
 | time axis 2026-03-09 to 2026-05-03
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Team Name and Logo | Dawud | 100% | 2026-02-02 | 2026-02-02 | 1
| Set-up Project Binder | Team | 100% | 2026-01-26 | 2026-02-08 | 14
| Customer Interview | Furqan, Bahja | 100% | 2026-02-03 | 2026-02-03 | 1
| Deliverable 1 |  |  | Week 1 | Week 6 | #VALUE!
| Use-case Diagram | Furqan, Haris, James, Bahja | 100% | 2026-02-05 | 2026-02-20 | 16
| Volere Templates | Bahja, Haris, Huzefa | 100%
| Use-case Specification | Dawud, Bahja, Haris | 100% | 2026-02-05 | 2026-02-12 | 8
| Prioritised List of Use Cases | Dawud, Furqan, Bahja | 100%
| Anticipated Evolution of system requirements | Faisal, Huzefa | 100%
| High-level Design (component diagram) | Furqan, James | 100%
| Class diagram of our subsystem | Huzefa, Faisal | 100%
| Generated source code with comments | Haris, Bahja | 100% | 2026-02-25 | 29/2/26
| Test cases | James | 100%
| Expected Hardware | Furqan | 100%
| Peer Review | Team | 100% | 2026-03-02 | 2026-03-08
| Deliverable 2 |  |  | Week 7 | Week 13 | #VALUE!
| Research |  |  | 2026-03-09 | 2026-03-13 | #NAME?
| GUI Implementation | Dawud, James, Haris, Furqan, Faisal | 100% |  |  | #NAME?
| Test Implementation | Furqan, Bahja, Huzefa, Dawud, Haris | 100% |  |  | #NAME?
| IPOS-PU-COMMS |  |  | 2026-03-09 | 2026-04-19 | #NAME?
| Accept SMTP requests | James |  |  |  | #NAME?
| Accept payment requests | James
| Make SMTP requests | Furqan, Faisal
| Make Stripe requests | Furqan, Faisal
| IPOS-PU-GUI |  |  | 2026-03-09 | 2026-04-19
| Commercial form | Furqan | 100%
| Non-commercial form | Furqan | 100%
| Login screen | Furqan | 100%
| Navbar | Furqan | 100%
| Merchant profile | Furqan
| Product list | Furqan | 100%
| Basket screen | Furqan | 100%
| Payment confirm screen | Furqan | 100%
| Admin dashboard | Furqan | 100%
| Report menu | Furqan | 100%
| Registration screen | Furqan | 100%
| Promotion feed | Furqan | 100%
| IPOS-PU-MEMBERS |  |  | 2026-03-09 | 2026-04-19
| Commercial form | Bahja | 100%
| Non-commercial form | Bahja | 100%
| Process commercial applications | Bahja
| Process non-commercial applications | Bahja
| User details database | Bahja | 100%
| Customer authentication | Bahja | 100%
| Change password | Bahja
| Prompt password change | Bahja | 100%
| Logout | Bahja
| Login | Bahja | 100%
| IPOS-PU-PRM |  |  | 2026-03-09 | 2026-04-19
| Promotion database | Huzefa
| Make promotion | Huzefa
| Cancel promotion | Huzefa
| Admin account | Huzefa
| Record clicks/sales | Huzefa
| IPOS-PU-RPT |  |  | 2026-03-09 | 2026-04-19
| Sales within a period | Faisal
| Ad campaign for a period | Faisal
| Hits of ad campaign | Faisal
| IPOS-PU-SALES |  |  | 2026-03-09 | 2026-04-19
| Filter catalogue | Haris | 100% | 2026-04-01 | 2026-04-06
| Add to cart | Haris | 100% | 2026-03-20 | 2026-03-23
| Confirm order | Haris, Dawud | 100%
| Checkout | Haris, Dawud | 100%
| Update order status | Haris, Dawud
| Check item for promotion | Haris, Dawud |  | 2026-03-26 | 2026-04-19
| Record items sold | Haris | 100% | 2026-04-02 | 2026-04-06
| Record items viewed | Haris | 100% | 2026-04-02 | 2026-04-06
| Calculate tax | Haris, Dawud | 100% | 2026-03-20 | 2026-04-15
| Update cart | Haris | 100% | 2026-03-20 | 2026-03-23
| Check 10th purchase discount | Haris, Dawud | 100% | 2026-03-26 | 2026-04-19
| Check promotion discount | Haris, Dawud | 100% | 2026-03-26 | 2026-04-19
| Make purchase | Haris, Dawud | 100%
| View cart | Haris | 100% | 2026-03-20 | 2026-03-23
| View item | Haris | 100% | 2026-04-01 | 2026-04-06
| Search catalogue | Haris | 100% | 2026-04-01 | 2026-04-06
| View catalogue | Haris | 100% | 2026-04-01 | 2026-04-06
| IPOS-PU-TEST |  |  | 2026-03-09 | 2026-04-19
| REST API tests | James
| IPOS-PU-DOCS |  |  | 2026-04-11 | 2026-04-26
| Implementation Report | Haris, Huzefa, Bahja, Faisal | 100% | 2026-04-12 | 2026-04-26
| Project Binder | Team | 100% | 2026-04-20 | 2026-04-26
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]