## Project schedule
| IN2033 Project | [5 empty] | Project start: | [7 empty] | 2026-01-26
| MediFlow Solutions |  | Project lead: Furqan |  |  |  | Display week: | [7 empty] | 1
[7 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-01-26 to 2026-03-22
 | time axis 2026-01-26 to 2026-03-22
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Team Name and Logo | Dawud | 100% | 2026-02-02 | 2026-02-02 | 1
| Set-up Project Binder | Team | 33% | 2026-01-26 | 2026-02-08 | 14
| Customer Interview | Furqan, Bahja | 100% | 2026-02-03 | 2026-02-03 | 1
Deliverable 1
| Use-case Diagram | Furqan, Haris, James
| Volere Templates | Bahja, Haris, Huzefa
| Use-case Specification | Dawud, Bahja, Haris | 100% | 2026-02-05 | 2026-02-12 | 8
| Prioritised List of Use Cases | Dawud
| Anticipated Evolution of system requirements | Faisal
High-level Design (component diagram)
Class diagram of our subsystem
Generated source code with comments
| Test cases | James
Expected Hardware
Deliverable 2
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]